## WRC
Scheme/Investment Name | Approved Completion Date | Forecast Completion Date
PR19 WINEP FFT UIMP5 Ramsey WRC | 2025-03-31 | 2025-08-17
PR19 WINEP FFT UIMP5 Dereham Rushmeadow Rd WRC | 2025-03-03 | 2025-09-29
PR19 WFD No Det: Stagsden WRC_P | 2024-06-29 | 2026-02-02
Peterborough Flag Fen WRC PR19 Growth Capacity | 2025-03-31 | 2025-11-10
CLOHST Clophill WRC PR19 Growth capacity | 2025-02-25 | 2025-04-10
NOCTST - Nocton RAF WRC PR19 Growth Flow | 2026-04-17 | 2026-04-17
Walton and Frinton Bathing Water Improvement WINEP WRC & PS | 2025-03-27 | 2025-10-07
PR19 WFD GES P_Faldingworth MOD WRC | 2024-12-22 | 2026-02-16
PR19 WFD GES P_Shudy Camps WRC | 2024-12-31 | 2025-05-06
Southwold WRC Bathing Water Improvements WINEP | 2024-12-31 | 2026-10-20
PR19 WFD GES P_Great Ponton WRC | 2025-01-28 | 2025-09-01
PR19 WFD GES P_Silk Willoughby WRC | 2024-09-24 | 2026-01-16
PR19 WFD GES P_Ridgewell WRC | 2025-05-27 | 2025-07-22
PR19 WFD GES P_Corringham WRC | 2024-12-22 | 2025-09-03
Foxton (Leics) WRC - Gartree Prison Development | 2025-03-31 | 2025-11-24
Langham WRC (Essex) LANMST DWF Compliance | 2025-03-31 | 2027-11-25
Norton (Suffolk) - DWF Compliance Growth | 2025-03-31 | 2026-02-17
PR19 WFD GES P_Everton WRC | 2024-12-22 | 2025-10-02
Bedford WRC DWF COMPLIANCE | 2025-03-31 | 2025-11-18
Southend WRC Odour Strategy | 2024-10-25 | 2026-10-15
PR19 WFD GES P_Coton WRC | 2024-05-29 | 2025-10-15
PR19 WFD GES P_Carbrooke-Church End WRC | 2024-12-22 | 2025-10-22
PR19 WFD GES P_Beachampton WRC | 2025-01-28 | 2025-05-07
PR19 WFD GES P_Old Weston Main Street WRC | 2024-12-22 | 2025-05-20
PR19 WFD GES P_Quendon STW | 2024-12-31 | 2025-10-23
PR19 WFD GES P_Toynton St Peter STW | 2025-01-28 | 2025-10-15
PR19 WFD GES P_Bradenham WRC | 2025-01-31 | 2025-08-05
PR19 WFD GES P_Dunton STW | 2024-12-31 | 2025-08-26
PR19 WFD GES P_Chippenham WRC | 2024-09-24 | 2025-06-24
PR19 WFD GES P_Upton WRC | 2025-02-25 | 2025-12-09